## Sheet1
Version Number | Planned Feature | Description | Done?
0.1.0-alpha | Spectrogram display |  | Yes
| Playback features |  | Yes
| Playhead scrolling |  | Yes
| (Rudimentary) File saving |  | Yes
| (Rudimentary) Main page |  | Yes
| Keyboard shortcuts |  | Yes
| JPackage integration |  | Yes
0.1.x-alpha | Bugfixes
| About window | Show the details about AudiTranscribe, incl. licence of AudiTranscribe and dependants' licences | Yes
| "Save File As" button | So that you can make a copy of the file
| README.md update |  | Yes
0.2.0-alpha | Toolbar options | These are the options that you see if you hover at the top of the window
| Settings page | To allow for customisation of default constants
Project searching / Project list
Progress bars
| Note playing | Make clicking on the spectrogram play the corresponding note
| Keyboard note playing | Use the first 2 rows of the keyboard
0.2.x-alpha | Bugfixes
Theme switching
0.3.0-alpha | BPM Estimation
Permit other audio files (not just WAV files)
Save audio data to file instead of relative audio path
| Music key approximation/estimation | Using machine learning
| Music note adding | Allow the adding of notes onto the spectrogram pane
0.3.x-alpha | Bugfixes
0.4.0-alpha | Automatic music transcription | Use the QTransform data to come up with an approximation of the music notes